## Лист1
COVID-19 self-assessment test
First Sprint
S.no | Task | Person Name | Hours | Sprint Status
1 | Over view Project Requirements | both |  | Done
2 | Paper Prototype | Ali |  | Done
3 | Setup Environment | Abhi |  | Done | finsih
4 | Solution Generations for UI | Ali |  | Done
5 | Home Page Complete creations | Abhi |  | Done
6 | Testing | Ali |  | Done
7 | Webpages Service and Your Health | Ali |  | Done
8
9
Second Sprint
S.no | Task | Person Name | Hours | Sprint Status
1 | Text decoration (webpages) | Abhi |  | Done
2 | Setup environment with Python (flask web ) | Ali |  | Done
3 | Incremental Testing/ find best solution for the system | Abhi |  | NOT DONE
4 | FAQ Page and subscription button with data base | Abhi |  | Database is reaming |  | finsih
5 | Page linking with Flask ( Service, health, result ) | Abhi |  | Done
6 | Create and deploy Self Assignment form and result page | Both |  | Done
7 | Write Content of coronavirus | Ali |  | Done
8 | black box Testing | Ali |  | Done
9 | Web pages contact us, live chat support | Abhi |  | UI Remains for Ali
10 | Create a "Scroll to Top" | Ali |  | Done
11 | Corona Data Fectch form API | Ali |  | Done some parts is remains
12 | Text decoration (webpages) | Ali |  | Done
13 | Page linking with Flask (Index, home, Stauts) | Ali |  | Done
14 | clone project and testing | both own systems |  | Done
15 | Demo Phase 1 | both |  | Done
16 | Self Assessement Trainning model (panda, numpy , logistics regression) | Abhi |  | Done
Third Sprint
S.no | Task | Person Name | Hours | Sprint Status
1 | Contact page create and link with falsk | Abhi |  | INPROGRESS | now Sprint
2 | Corona Database Fetch form Api | Ali |  | INPROGRESS
3 | Current Status UI and Link with flask | Ali |  | INPROGRESS
4 | live chat integration with contact page and falsk | Abhi |  | INPROGRESS
5 | Database intergrate with Flask gun and Contact page together | Both |  | INPROGRESS
6 | Contact form with Database | Abhi |  | INPROGRESS
7 | Write Content of Status and Add Features | Both |  | INPROGRESS
8 | Test moudle and all pages | Both |  | INPROGRESS
9 | Integration Testing Phase 1 (User input in self Ass test) | Abhi |  | INPROGRESS
10 | Integration Testing Phase 2 (User input coutnry name and status) | Ali |  | INPROGRESS
11 | Add some features in Yourhealth Page | Abhi |  | INPROGRESS
12 | test the interface after intergration all Web pages with flask | both |  | INPROGRESS
13 | chat boot falsk intergraiton with Flask main system | Ali |  | INPROGRESS
14 | live chat win size and pop up | Abhi |  | INPROGRESS |  |  | 6
15 | Create tables with filter (cities contact number ) | Ali |  | INPROGRESS
Forth Sprint
1 | intergration phase 2
2 | Full intergration System
3 | Publish help Content